## Current
Multi-Year Plans 2018-2023
Physical and Architectural Barriers
Barrier Identified | Actions to be Taken | Accountability | Timelines | Status
First and Second Floor student tables in the Library need height adjustable desks in the common work area | Purchase height adjustable desk | Library | 2018-2023 | To be completed
Access catalogue table is too high in the Library | Lower table or install height adjustable table | Library/Physical Plant Department | 2018-2023 | To be completed
In the Library only Study Room H is accessible, other study rooms do not have automatic doors | Install automatic door openers | Physical Plant Department | 2018-2023 | To be completed
In the Library 2nd Floor restrooms the paper towel dispensers are installed too high | Lower the paper towel dispensers | Physical Plant Department | 2018-2023 | To be completed
Library 2nd floor washrooms the stall door handles are too small to maneuver for those with hand grip issues | Install lock that can be maneuvered with a closed fist | Physical Plant Department | 2018-2023 | To be completed
Books and library materials are not accessible for visually impaired persons | All items should be available in digital format | Library | 2018-2023 | To be completed
Main level photocopiers in the Library are not accessible for persons in a wheelchair | Replace one photocopier with a lower machine/connect a scanner to the photocopier and place on a lower table | ITS/Library | 2018-2023 | To be completed
The East/West sidewalk at Wemple are uneven | Build up ground area to make level with sidewalks | Physical Plant Department | 2018-2023 | To be completed
Main entrance of Wemple displays maps that lack accessibility information | Replace with maps that provide accessibility information | Physical Plant Department | 2019-2020 | To be completed
Door to student lounge extension in Wemple does not have an automatic door opener | Add an automatic door opener | Physical Plant Department | 2018-2023 | To be completed
Student lounge extension hallway is too narrow and used for furniture storage | Clear enough space for wheelchair and scooter access | Physical Plant Department | 2018-2023 | To be completed
Wemple Computer Lab W022 has no accessible desk, no height adjustable desk and the outlets are not accessible by being too high | Remove a chair from a desk, acquire one adjustable desk and lower some outlets to be accessible | Physical Plant Department/ITS | 2019-2020 | To be completed
Chapel has no automatic door sign | apply sign to door | Physical Plant Department | 2018-2019 | To be completed
Inner Courtyard by Cafeteria/W022 Entrance does not have an automatic door opener | Add an automatic door opener | Physical Plant Department | 2018-2023 | To be completed
Wemple Cafeteria the Condiments are not accessible | Condiments are placed in the back, containers should be moved forward | Aramark | 2018-2023 | To be completed
Wemple East wing male and female washrooms the paper towel dispensers are too high | Lower dispenser | Physical Plant Department | 2018-2023 | To be completed
East exit to Courtyard is not accessible by wheelchair | Install a ramp and automatic Door | Physical Plant Department | 2018-2019 | To be completed
Wemple Courtyard area with picnic tables and gazebo are on grass and inaccessible for chairs and scooters | Install pathways | Physical Plant Department | 2018-2019 | To be completed
Condo 265 needs an accessible bedroom | Renovate to add main floor bedroom | Physical Plant Department | 2018-2019 | To be completed
Condo 265 ramp at front door needs repair | Improve the accessibility ramp | Physical Plant Department | 2018-2019 | To be completed
Condo 265 main floor washroom not accessible | Renovate main floor washroom for accessibility | Physical Plant Department | 2018-2019 | To be completed
Labatt Hall needs an auto door opener for 2nd floor washroom | Install an automatic door opener | Physical Plant Department | 2018-2019 | To be completed
Labatt Hall room 203 needs an auto door opener | Install an automatic door opener | Physical Plant Department | 2018-2019 | To be completed
Labatt Hall needs an auto door opener for east hallway to mail boxes | Install an automatic door opener | Physical Plant Department | 2018-2019 | To be completed
Stairwell in Labatt Hall does not have nosings installed so is dangerous to those with depth perception issues | Apply contrasting strips | Physical Plant Department | 2018-2019 | To be completed
LH 105A has a ramp that leads outside, needs an accessible door button | Accessible door button | Physical Plant Department | 2018-2019 | To be completed
Lack of signage at the front of buildings indicating accessible entrances | Install signs | Physical Plant Department | 2018-2023 | To be completed
Ensure all classrooms have an accessible seating spot and that podiums are placed in such a way to be accessible | Ensure no chairs are placed there, perhaps place accessible symbol on the desk. Also ensure podiums have space to move around for wheelchair access | Physical Plant Department | 2019-2020 | To be completed
Epworth Houses need a lowered counter space in the kitchen | Lower kitchen counter | Physical Plant Department | 2017 | To be completed
King's Center nosings on south east entrance to pit are worn out | Replace nosings | Physical Plant Department | 2018-20203 | ongoing
No height adjustable desks in the Learning Commons and Lounge Areas in the King's Center | Ensure there is at least one height adjustable desk | Physical Plant Department | 2019 | To be completed
King's Center Main area, lounges and learning commons do not have any accessible outlets | Install some accessible power outlets | Physical Plant Department | 2018-2023 | To be completed
King's Center Fire exit signs are suspended signs difficult to read (clear/see through) | Place a border around signs | Physical Plant Department | 2018-2023 | To be completed
KC 006 a height adjustable desk is located at front, right side of room & awkward to access for a chair/scooter | Move to front left of room as it will be easier to access for a person using a chair | Physical Plant Department | 2018-2023 | To be completed
KC 004 Height adjustable desk is difficult to access, not enough space | Moved to front row, but still awkward to access. Accessible desk should be placed on the outside row. | Physical Plant Department | 2018-2023 | To be completed
KC 004 Door does not open automatically when button is pushed handle must be used | Adjust so only button is needed to open door | Physical Plant Department | 2018-2023 | To be completed
KC 004, 005, 006 Automatic doors give access to courtyard area only. Must use stairs if you wish to access campus. | Post a sign stating door leads to courtyard only; use of stairs required to reach other areas of campus | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area new accessible bike is located next to a pillar, and therefore only accessible on one side | Move to a different location so that an individual may transfer from either side | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area it is necessary to tap card, push the accessible button and open door at the same time to gain entry which is very awkward | Have door open automatically when button pushed after card swiped | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area bathroom has no “automatic door sign” | Apply sign to door | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area female bathroom the soap dispenser is in accessible, located on mirror, between sinks and inaccessible | Move to an accessible location, e.g.. to right of garbage bin | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area clothing and towel hooks are inaccessible as they are too high and the bench is in the way | Move some to an accessible location | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area telephone is inaccessible as a bench is located in front of phone | Move bench | Physical Plant Department | 2018-2023 | To be completed
King's Center Fitness Area lockers in change room inaccessible, blocked by bench | Move bench to another area, or shorten so that some lockers are accessible | Physical Plant Department | 2018-2023 | To be completed
King's Center lower level, accessible restroom has no “automatic door sign” | Apply signage to door | Physical Plant Department | 2018-2023 | To be completed
King's Center lower level accessible restroom the accessible door opener is not always accessible when the hallway door is left open, it blocks the accessible button | Ensure door is not left open, or move button | Physical Plant Department | 2018-2023 | To be completed
King's Center south exit by Café '54 the accessible door opener is awkward to access as it is blocked by people lining up at Café ‘54 | Move to a different location | Physical Plant Department | 2018-2023 | To be completed
King's Center Café '54 refrigerator door is difficult to open door during the summer months as condiment table blocks access | Move condiments to another location | Physical Plant Department | 2018-2023 | To be completed
King's Center learning commons ramp is too steep | Needs grading | Physical Plant Department | 2018-2023 | To be completed
King's Center all bannisters are made of metal with sharp edges | Can cause injury is gripping tightly to prevent a fall | Physical Plant Department | 2018-2023 | To be completed
King's Center elevator doors closes very quickly | Adjust timing on doors | Physical Plant Department | 2018-2023 | To be completed
King's Center 207 no “automatic door sign” | Apply signage to door | Physical Plant Department | 2018-2023 | To be completed
King's Center meeting room doors none are accessible | Install automatic openers on some / all of the meeting rooms | Physical Plant Department | 2018-2023 | To be completed
King's Center all accessible door bars are difficult to use, especially for those with limited foot movement | Switch to non bar accessible doors | Physical Plant Department | 2018-2023 | To be completed
Walkways north of crosswalk to Labatt Hall have uneven surfaces | Walkway is uneven and made of different materials. Concrete is cracked and needs repaving | Physical Plant Department | 2021 | To be completed
Dante Leonardon front entrance is inaccessible. | No ramp and door needs an automatic opener. | Physical Plant Department | 2018-2023 | To be completed
DL 112 and DL 114 door is inaccessible | Needs a door opener | Physical Plant Department | 2018-2023 | To be completed
Dante Leonardon back entrance is inaccessible | No ramp and door needs an automatic opener. | Physical Plant Department | 2018-2023 | To be completed
Dante Leonardon front and rear entrances need nosings for visually impaired persons | Paint yellow strip on stairs | Physical Plant Department | 2018-2023 | To be completed
Stairwell leading to the basement in Dante Leonardon is poorly lit making it dangerous for visually impaired people to traverse up and down the stairs | Replace with brighter bulbs/add more lighting | Physical Plant Department | 2018-2023 | To be completed
DL012 Classroom no nosings on the edge of stairs | Needs nosings | Physical Plant Department | 2018-2023 | To be completed
DL 210 counter is not accessible | A section will need to be lowered to make accessible | Physical Plant Department | 2021 | To be completed
Academic Dean's Office Waiting area does not have a space for a person to wait in a wheelchair | Remove a chair and create a space for a wheelchair | Academic Dean's Office | 2018 | To be completed
Annex Psychology Labs have stairs making the rooms inaccessible for persons in wheelchairs and the stairs have no nosings making it dangerous for visually impaired persons | Install ramp and paint nosings on stairs | Physical Plant Department | 2018-2023 | To be completed
Annex 3rd floor hallway very narrow and may be inaccessible for wider scooters and chairs | Post a sign at the elevator indicating maximum width | Physical Plant Department | 2018-2023 | To be completed
Annex 3rd floor lift has a pull door and is key operated | Install remote opener and keypad operating system | Physical Plant Department | 2018-2023 | To be completed
SA 060 Classroom is accessible only in the back. Stairs are required to reach front of room | Can a ramp be installed? | Physical Plant Department | 2018-2023 | To be completed
Faculty Building path and ramp to the entrance the incline is very steep | Can it be graded appropriately or can an alternative route to the Faculty Building be created | Physical Plant Department | 2018-2023 | To be completed
Faculty Building Entrance does not have signage indicating classroom and room locations | Create a post signs by front door | Physical Plant Department | 2018-2023 | To be completed
Faculty Building second floor washrooms do not have auto door openers | Install automatic door openers | Physical Plant Department | 2018-2023 | To be completed
Faculty Building Emergency exit west side is inaccessible | Install accessible buttons at doors from hallway to stairwell area, and on exit. Install ramp exit to outdoors. | Physical Plant Department | 2018-2023 | To be completed
Broughdale Hall the elevator doors close to quickly to exit safely | Adjust timing on doors | Physical Plant Department | 2018-2023 | To be completed
BH006 Door to MSW Student Room is inaccessible | Install automatic door openers | Physical Plant Department | 2018-2023 | To be completed
BH006 Foyer chairs are being placed in doorways limiting access | remove chairs from entrances | Physical Plant Department | 2018-2023 | To be completed
Broughdale Hall 2nd floor landing near elevator risers are solid, clear and makes it difficult to judge depth perception | Apply nosings | Physical Plant Department | 2018-2023 | To be completed
Broughdale Hall Lower level Lounge the hand sanitizer dispenser is too high | Lower | Physical Plant Department | 2018-2023 | To be completed
Broughdale Hall lower level lounge area the phone is too high | lower | Physical Plant Department | 2018-2023 | To be completed
Information and Communication
Course Outlines are not in accessible formats | Training staff and faculty in how to create word and PDF documents in accessible formats. Ensuring existing documents are edited for accessibility | ITS and HR | 2018-2023 | To be completed
Need accessible formats for fire safety plans | Ensure fire safety plans are available in accessible formats and available on the website | HR/ITS |  | To be completed
Develop a feedback form as part of the requirements for integrated standards so that the community can provide feedback to the committee | Currently able to do with email, perhaps other forms could be explored, tweeting, texting, forms. | HR/ITS |  | To be completed
Customer Service Barriers
Student employees need to receive AODA training | Follow up needed with leaders to ensure their student staff are trained at time of hire | HR | 2018-2023 | Ongoing
Student Council and student leaders should received training in AODA | Student Affairs will monitor and ensure training is offered and completed | Student Affairs | 2018-2023 | To be completed
Attitudinal Barriers
Student Leaders should receive mental health training that addresses reducing barriers for students with MH issues | Have a central location that arranges the training | Student Affairs | 2018-2023 | To be completed
Need for an Accessibility Committee that advocates for disabled members of our community | Create an accessibility committee and meet regularly to discuss accessibility issues | HR | 2018-2023 | Ongoing
Websites must meet the requirements for Accessibility under the standards | To be completed updating and monitoring of sites to ensure it meets obligations under AODA | ITS | 2018-2021 | Standard to be completed by 2021
Policies and or Practices Causing Barriers
Create a Duty to Accommodate Policy | For employees to clearly see accommodation goals of the organization | HR | 2018-2023 | To be completed
Employment Barriers
Employees who have identified themselves as having a disability must have an individualized emergency response plan in necessary | HR to respond to such requests in a reasonable timeframe, document the plan and keep in employee file | HR | 2018 | To be completed
Individualize emergency response plans for employees that identify a disability and that they require a personalized plan | Communicate and encourage any employee with a short or long term disability to meet with HR to discuss emergency planning and accommodation plans | HR | 2018 | To be completed
Emergency plans, procedures and building maps are not easily found | Make the plans easier to find and intuitive | HR | 2018 | To be completed
An individualized accommodation plan that is reviewed regularly for employees who have identified themselves as having a disability must have | HR to respond to such requests in a reasonable timeframe, document the plan and keep in employee file, and schedule reviews of plan with employee | HR | 2018 | To be completed
Lack of a Duty to Accommodate Policy | Create a duty to accommodate policy in line with AODA standards and best practices | HR | 2018 | to be completed
Training for leaders on how to support employee with a disability in performance. | Create a training package for leaders | HR | 2018-2023 | To be completed
Transportation Barriers
Built Environment Barriers
There are some inaccessible classrooms and they should be noted to ensure those with accessibility needs are not assigned to those classrooms: Dante Leonardon 130, Dante Leonardon 012 & South Annex 060 | The building is older, installing accessible equipment is not feasible. However any renovations to the building, accessibility will be forefront. | Physical Plant Department | 2018-2023 | To be completed
Lack of a universal washroom with an adult change table | Universal washroom and adult change table to be installed in new buildings or newly renovated buildings as necessary | Physical Plant | 2018-2023 | To be completed
Lack of accessible outside public eating areas. | Ensure 1 table is accessible, and the ground leading to the table is firm and stable and there are spaces for mobility aids. | Physical Plant | 2018-2023 | To be completed
Not all Fire Exits have automatic door openers | Ensure doors to fire exits are automatic, or at minimum door handles should have levers. | Physical Plant | 2018-2023 | Ongoing
Suitable and enough accessible parking | Parking spots must be maintained and must have an adequate number. Also at the Wemple building large trucks park and cut off accessible parking, must ensure cars can get in and out. | Physical Plant | 2018-2023 | To be completed
Wemple East Wing Lift is small and very tight for an individual who uses a chair, with a service dog / or attendant. Use of key to operate seems unnecessary | Need to renovate and make a larger lift, also the signage should be replaced with "Call security for lift key…" | Physical Plant Department | 2018-2023 | To be completed
Student Affairs waiting room is too small to accommodate more than one wheel chair or scooter and the doorway is narrow and does not meet FADS Standards | Suggest move waiting room to a larger space with a wider doorway in the future | Physical Plant Department/Student Affairs | 2018-2023 | To be completed
Wemple second floor faculty offices are not accessible | Ensure faculty will meet with students to whom accessibility is an issue elsewhere. Do not assign faculty who require mobility aids to the offices. Can renovations be accomplished for elevator access? | ADO/Physical Plant | 2018-2023 | To be completed
Residence Office entrance needs to be made accessible for physical access | Redo the entrance or signage with instructions for accessing the Office through Alumni Court Residence+B86 | Physical Plant Department | 2020-2021 | To be completed
All areas Ensure all entrance doors and washroom doors are accessible | Ensure equipped with auto door openers | Physical Plant Department | 2018-2023 | To be completed
All areas hallways, entrances for offices need to be made wide enough for wheelchairs | Ensure hallways and offices are configured for wheelchair access | Physical Plant Department | 2018-2023 | To be completed
All areas ensure all curbs have ramps | Upkeep is critical | Physical Plant Department | 2018-2023 | To be completed
All areas accessible counters at all service desks | All service counters must have at least one accessible counter | Departments/Physical Plant Department | 2018 | completed
All areas all waiting areas must be accessible | Ensure seats are not fastened to the ground and there is at least one accessible chair | Departments/Physical Plant Department | 2018-2023 | To be completed
All areas where queuing lines are required ensure the fixed waiting line is wide enough for people with disabilities to move through easily with their mobility aids | Wide enough hallways for those in power chairs, wheelchairs and scooters and areas to tap canes to find the beginning and end of queuing lines | Departments/Physical Plant Department | 2018-2023 | To be completed
All areas fire alarms are not suitable for people with hearing impairments | On identified floors, ensure smoke alarms are equipped with visual cues | Departments/Physical Plant Department | 2018-2023 | To be completed
All areas washroom dryer and sink must be mounted for wheelchair accessibility | Renovating washrooms as necessary | Physical Plant Department | 2018-2023 | To be completed
REVISED FEBRUARY 2019

## Completed Items
COMPLETED
Physical and Architectural Barriers
Barrier Identified | Actions to be Taken | Accountability | Timelines | Status
FB003, FB110, BH 107, BH 108, BH 109, BH 112 Doors are inaccessible | Install an automatic door opener | Physical Plant Department | 2015 | completed
Wemple lower level entrance to the cafeteria is too close to the door as it opens toward the individual and is awkward to reach | move button to more accessible location | Physical Plant Department | 2016 | completed
Wemple east wing male and femal restrooms soap dispensers were inaccessible for persons in chair | Moved to an accessible location | Physical Plant Department | 2016 | completed
Wemple window by lower level entrance to cafeteria the video surveillance sign blocks view to parking lot for an individual in a chair who may be watching for transportation | Move the sign to a different location | Physical Plant Department | 2016 | completed
W022 entrance, chairs were placed in front of the accessible button | Chairs to be removed | Physical Plant Department | 2016 | completed
LH 105 Replace ramp due to wood being worn and splitting | Replace ranp | Physical Plant Department | 2016 | completed
Access to "pit" from King's center has no contrast strips | Entire entrances has been renovated and converted to stairs with nosings and railings | Physical Plant Department | 2016 | completed
KC006 Ergonomic Chair placed at front of room near instructor's desk | Place in a location in the room where a student could eaily access if necessary | Physical Plant Department | 2016 | completed
Labatt Hall 101 and 103 signs needed to denote accessible door | Apply sign | Physical Plant Department | 2016 | completed
Kings Center 005 needs a height adjustable desk. Located at the front, on the left and diffcult to access for a chair/scooter | Move to the right of the center aisel | Physical Plant Department | 2016 | completed
Kings Center stairs the contrast strip does not provide enough contract | apply yellow nosings | Physical Plant Department | 2016 | completed
Library west side og building the sairs to parking lot need repainted of the nosings | repaint | Physical Plant Department | 2016 | completed
Library study room H door needs sign for automatic door | apply sign | Physical Plant Department | 2016 | completed
Physical and Architectural Barriers
Dante Leonardon ADO waiting room and entrance to DL the accessible door needs sign | Apply sign | Physical Plant Department | 2016 | completed
Student identified accommodation needs for accessibility in residence as needed | Modified residence room to accommodate student accessibility needs | Physical Plant Department/Student Affairs | 2017 | completed
Upper residence in Epworth Place Houses are not accessible currently | Provided greater accessibility as needed | Physical Plant Department/Student Affairs | 2017 | completed
Alumni Court main floor kitchen needs a lowered counter for accessibility | Lower kitchen counter | Physical Plant Department | 2017 | completed
Labatt Hall 2nd floor restrooms the doors need an automatic door opener | Install an automatic door opener | Physical Plant Department | 2017 | completed
Wemple Vitali Lounge Door needs sign for autmatic door | Apply sign | Physical Plant Department | 2018 | completed
Wemple reception needs sign for autmatic door | Apply sign | Physical Plant Department | 2018 | completed
Labatt Hall main entrance needs an accessbile door sign | Apply sign | Physical Plant Department | 2018 | completed
Labatt Hall SW main office the counters are too high | Lower Counter | Physical Plant Department | 2018 | completed
Labatt Hall Entance to 212-215 no automatic door opener | Install an automatic door opener | Physical Plant Department | 2018 | completed
Dante Leonardon front and rear entrances the stairs need nosings | Apply nosings | Physical Plant Department | 2018 | completed
Library needs an auto door opener for 2nd floor washroom | Install an automatic door opener | Physical Plant Department | 2018-2019 | completed
Library needs an auto door opener for 2nd floor shelter in place | Install an automatic door opener | Physical Plant Department | 2018-2019 | completed
Shelter in Place signs in various doorways lack further information or procedures | Need to provide more information in the shelter | Physical Plant Department | 2018-2023 | completed
Wemple East Wing posted sign by the lift provides little information | Remove blue & white signs and replace with better information e.g.. “Call Security for lift key 519-521-6215. A phone is located on opposite wall” | Physical Plant Department | 2018-2023 | Completed
Wemple East Wing by lift phone does not work | Fix phone | Physical Plant Department | 2018-2023 | Completed
Wemple lower level fire door by cafeteria has no automatic door sign | apply sign to door | Physical Plant Department | 2018-2019 | Completed
Information and Communication
Assisted device for projection has been identified as a need in at least one access lab | Installed in Access Lab 3 for students to use for school work, projects, presentations and accommodated exams | ITS /Student Affairs | 2017 | completed
Lack of access to the accessibility software Inspiration mind for students with accessibility recommendations | Software is now available on all student facing public use computer terminals, as well as the W022 computer lab, library, and W143 computer lab | ITS /Student Affairs | 2017 | completed
Lack of access to the accessibility software Kurzweil 3000 for students with accessibility recommendations | Software is now available on free to all qualifying SSD students | Western U/ITS/Student Affairs | 2017 | completed
Customer Service Barriers
In order to better serve our community we need to ensure we have access to best practices and up to date research | Our Assistive Technologist has joined the board of The Ability First Coalition which aims to increase employment opportunities for those with disabilities | Student Affairs | 2017 | completed
Ongoing Training of staff and faculty on AODA standards and best practices | Various in-service Assistive Technology trainings have been delivered to campus units and community partners | Student Affairs | 2017 | completed
Attitudinal Barriers
Need for increased awareness around mental health and wellness for students | Creation of a Mental Health and Wellness Committee | Student Affairs | 2018-2019 | completed 2018 committee struck
Technological Barriers
Work surfaces and computer monitors need to be adjustable in all access labs | Install mounted on articulating ergotron arms and motorized height adjustments for desks | ITS/Student Affairs/ Physical Plant Department | 2017 | completed
Need more equipment to loan to SSD students | Purchase more loaner equipment such as laptops, Live Scribe Pens, headsets and various software | ITS/Student Affairs | 2017 | completed
Students bothered by noise during accommodated exams | Ear cancelling head phones have been purchased | Student Affairs | 2017 | completed
Policies and or Practices Causing Barriers
To ensure that policies and practices keep in mind AODA standards and best practices | Creation of an AODA Committee to monitor this | HR | 2018 | Completed
Create an Accessibility Policy | reaffirm King's commitment and policy statements | HR | 2018 | Completed
Increase access to on campus resources through assistive technology and accessible workspaces | Create a specialized reservation system for the Access Labs through the Assistive Technologist | Student Affairs/IT | 2017 | complete
Ensure that students with disabilities have better access to on campus assistive technology and accessible workspaces | Creation of a specialized reservation for Access Labs through bookings with the assistive technologist | Student Affairs/IT | 2017 | complete
Ensure that our Goods and Service providers are compliant with AODA and put accessibility first | Revise our Policy on purchasing goods and services to reflect the AODA principals of Integrated Standards | Finance | 2014 | complete
Employment Barriers
Inform potential candidates that accommodations are available upon request | Statement posted online and recruiters when setting up interviews to share with candidates that we are an accessible campus | HR | 2014 | completed
Transportation Barriers
Transportation at King's is contracted through an outside company | Ensure that the company has an up to date AODA policy and trains their employees | HR/Finance | 2018 | completed
Built Environment Barriers
Additional Student Access Labs in Student Life Center needed | With the opening of AL: a) 2 additional student Access Lab computer systems b) 4 motorized height adjustable work station desks c) 2 ergonomic chairs | Physical Plant Department/ITS/Student Affairs | 2017 | completed
Built Environment Barriers
Assistance buttons required in all access labs | Install assistance button in all three labs | Physical Plant/Student Affairs | 2017 | completed
Need for a signal for proctor assistance in accommodated exam situations | Purchase and install a wireless door bell system | Physical Plant/Student Affairs | 2017 | completed